{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Blad1"],"not_rendered":{"charts":0,"images":2,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Blad1","index":0,"n_rows":89,"n_cols":14,"rows_kept":89,"cut":false,"hidden":false,"merged":[]}
[]
[]
["EQUIPMENT & WEIGHT CALCULATION"]
[]
["Client:",null,"Flott Gjort"]
["Project:",null,"Airstream burger trailer"]
["Status:"]
["Max weight:",null,3500,"kg"]
["Caculated weight finished:",null,{"$f":"E77","v":2810.55},"kg"]
[]
["Position","Desciption","Brand","Model","Weight (kg)","Width (mm)","Depth (mm)","Heigth (mm)","kW 230V","kW 400V","Water supply","Use","Delivery time","Remarks"]
[{"$nulls":8},"alles boven de 3,6 \nKW is 400 V"]
["BASE"," "]
[null,"AIRSTREAM","NLC",null,2000]
[]
[null,"VLOER","Buitelaar",null,0,{"$nulls":7}," "]
[null,"WANDAFWERKING","Buitelaar",null,0]
[null,"VLOERPUTJES","Buitelaar",null,0]
[null,"DEURSLOT OPBOUW HEAVY DUTY","Buitelaar",null,0]
[]
[{"$nulls":4}," "]
["EQUIPMENT"]
[1,"KOELWERKBANK ","Electrolux Professional",710053,143,1795,700,850,0.3,"-",null,null,"11 mei","9/5 bevestigd dat de levertijd 11.05 is."]
["2022-03-02","FRITUUR 2x15 L","Zanussi / Hakvoort",45021072,81,800,700,850,"-",17.399999999999999,null,null,"Geleverd"]
["2022-03-02","FILTER VOOR OLIE OPVANGBAK","Electrolux Professional",921693,"-","-","-","-","-","-",null,null,"Geleverd","Deze houden wij iol met Raymond. Deze filter past op Zanussi en bespaart 35% vetkosten op jaarbasis"]
["2022-03-02","VENTILATIE KANAAL VERHOGING","Electrolux Professional",206304,"-","-","-","-","-","-",null,null,"6 mei","RETOUR, Mail is verstuurd"]
[4,"WARMHOUDBAK","Zanussi / Hakvoort",45061000,20,400,700,250,1,"-",null,null,"Geleverd"]
[4,"OPEN ONDERBOUWKAST VOOR WARMHOUDBAK","Zanussi / Hakvoort","4510.1002",10,"400","550","600","-","-",null,null,"Geleverd"]
[4,"DEUR TBV ONDERSTEL ","Zanussi / Hakvoort","3451.500",6,"400","-","-","-","-",null,null,"Geleverd"]
[5,"SALADETTE","Nordcap","PA 13-150",51,1500,395,"225/434",0.112,null,null,null,"17 mei"]
[6,"BAKPLAAT ","Zanussi / Hakvoort",45011055,70,800,700,250,"-",8.4,null,null,"Geleverd"]
[7,"BAKPLAAT ","Zanussi / Hakvoort","45011055",70,800,700,250,"z",8.4,null,null,"Geleverd"]
[8,"WARMHOUDKAST (HOLDING CABINET)","Alto Shaam","500-3D",68,624,657,664,0.6,"-",null,null,"Geleverd"," "]
[9,"TAFELMODEL KOELKAST","Liebherr ","FKUV1610",37,615,620,830,0.1,"-",null,null,"Geleverd"]
[10,"TAFELMODEL KOELKAST","Liebherr ","FKUV1610",37,615,620,830,0.1,"-",null,null,"Geleverd"]
[17,"KOELONDERBOUW MET 3 LADES","Nordcap","46711113002-0-N-0",155,1600,700,705,0.18,null,null,null,"Geleverd","Opgehaald door Joey"]
[18,"AFZUIGKAP 150 + 200cm ","Hakvoort"," ","d","1500/2000",600,"250/600",{"$nulls":4},"Geleverd"]
[18,"RVS LAMELLENFILTER","Hak Proffesional","2054.122",5,480,450,25,"-","-",null,null,"Geleverd"," "]
[18,"DAKMOTOR","HANS / BM"," ",{"$nulls":8},"Nog niet bekend"]
["DIV","MARINE STELPOTEN XXXXX STUKS","Electrolux Professional",880326,2.5499999999999998,null,null,null,"-","-",null,null,"Geleverd"," "]
[null,"SOFTISMASKIN CAPRINANI","Capriani",null,50]
["FURNITURE"]
[11,"WASBAK VOOR HANDEN","NLC",null,5,600,600,{"$nulls":5},"Geleverd","Voorbeelden per email 10/4 naar Leon"]
[12,"KAST DROGE SPULLEN","Hutte",null,0,"Maatwerk op basis van beschikbare ruimte",{"$nulls":7},"Maatwerk Hutte Bouwers"]
[13,"UITGIFTECOUNTER BETONPLEX / EIKEN","Hutte",null,0,"Maatwerk op basis van beschikbare ruimte",{"$nulls":7},"Maatwerk Hutte Bouwers"]
[14,"WERKBLAD MET OPSTAANDE RAND V.V. SPOELBAK","Buitelaar",null,0,"Maatwerk Leon / BM",{"$nulls":7},"Maatwerk Buitelaar"]
[15,"WERKBLAD MET OPSTAANDE RAND ","Buitelaar",null,0,"Maatwerk Leon / BM",{"$nulls":7},"Maatwerk Buitelaar"]
[16,"LAGER DEEL UITGIFTECOUNTER AAN BUITENZIJDE","Hutte",null,0,"Maatwerk op basis van beschikbare ruimte"]
[20,"TAFEL BUITEN LINKS","Hutte",null,0,"Maatwerk op basis van beschikbare ruimte"]
[21,"TAFEL BUITEN RECHTS","Hutte",null,0,"Maatwerk op basis van beschikbare ruimte"]
[22,"WERKBLAD ","Buitelaar",null,null,"Maatwerk Leon / BM",{"$nulls":7},"Maatwerk Buitelaar"]
[23,"RVS WANDAFWERKING + HITTESCHILD","Buitelaar",null,null,"Maatwerk Leon / BM"]
[24,"WERKTAFEL","Buitelaar / Hutte",null,null,"Maatwerk Leon / BM",{"$nulls":7},"Maatwerk Buitelaar"]
[]
["ELECTRICAL INSTALLATION"]
[19,"ACHTERUITRIJCAMERA","Hutte (Sjoerd)",null,0,"VERVALLEN"]
[26,"VOLLEDIGE ELEKTRISCHE INSTALLATIE OP 63A 400V","Hans de Jong",null,0]
[]
[]
["WATER INSTALLATION"]
[25,"WATERAANSLUTING + DRUKREDUCEER UNIT","Buitelaar",null,0]
[{"$nulls":4},0]
[]
["CLIMATE"]
[null,"NIET VAN TOEPASSING",null,null,0]
[]
["ICT"]
[null,"NIET VAN TOEPASSING",null,null,0]
[]
["STOCK"]
[null,"NIET VAN TOEPASSING",null,null,0]
[]
["MISCALANEOUS"]
[null,"VEILIGHEIDSMIDDELEN",null,null,0]
[]
[]
["FORECAST WEIGHT",null,null,null,{"$f":"SUM(E14:E75)","v":2810.55}," "," "]
[]
[]
[]
[]
[null," "]
[null," "]
[null," "]
[null," "]
[null," "]
[null," ",null," "]
[null," "]
[null," "]